## Format Logframe
Logframe
Project Title:
Project Manager:
Project Number: |  | Term of Project:
Indicators
| Description | Indicators | Comments / Assumptions
Goal
Outcome
Output 1
Activity 1.1
Activity 1.2
Activity 1.3
Output 2
Activity 2.1
Activity 2.2
Activity 2.3
Output 3
Activity 3.1
Activity 3.2
Activity 3.3

## Example Logframe
Logframe
Project Title:
Project Manager:
Project Number: |  | Term of Project:
Instructions
|  | Indicators | Indicators have to be SMART! (Specific, Measurable, Achieveable, Realistic and Timely) and with target values
| Description | Indicators | Indicators have to be SMART! (Specific, Measurable, Achievable, Realistic and Timely) and include target and if possible baseline values
Goal | To contribute to improved health of women in the xxx region |  | Goal: The higher-order objective to which a project is intended to contribute
Outcome | The obstetrical healthcare services are improved | By end of xx, the number of obstetrical complications (hemorrhages, infections, eclampsia) per year has decreased by xx % compared with the baseline | Outcome: The achieved short-term and medium-term effects / end results of a project.
Output 1 | The number of institutional births in region XY is increased | 1.1. The number of institutional births at hospital X and the 6 peripheral health centers has increased each year by xx % | Outputs (maximun three): The products, capital goods and services which result from a project; may also include changes resulting from the intervention which are relevant to the achievement of the outcome.
Activity 1.1 | Identify barriers to access in the project area |  | For ease of reference between the EXCEL budget and the logframe, please use the same numbering for the activities in both documents.
Activity 1.2 | Establish an action plan together with the District Health Management Team to address the barriers
Activity 1.3 | Conduct one awareness campaign to reach xxx people in the first six months
Output 2 | Medical equipment and essential medications at hospital X are available | 2.1. The equipment applied for is procured by xxxx 2.2. Continuous availability of essential obstetric medicines is demonstrated on a monthly basis
Activity 2.1 | Agree on procurement guidelines to be followed
Activity 2.2 | Get price quotes and order equipment by end of xxx
Activity 2.3 | Send stocklist of essential medicines to project manager every month
Output 3 | A continuous training program for the midwives at hospital X and the 6 associated health centers is established | 3.1. The 12 midwives at hospital X and the 6 midwives at the 6 health centers have taken part in 3 two-day workshops regarding BEmOC by October 2023 3.2. The 6 midwives at the centers receive supportive supervision on 1 day/month via trained coaches from the hospital
Activity 3.1 | Select and train two trainers to conduct workshops and supervison
Activity 3.2 | In the first year, implement one two-day workshop every four months
Activity 3.3 | Agree on a clinical supportive supervison checklist and start supervison after the first workshop